PROPOSAL

Regional Landscape Mapping

for Pfizer Sweden

A comprehensive overview of healthcare governance, budget allocation, demographics, and pharmaceutical utilisation across all 21 Swedish regions.

| Prepared for | Pfizer Sweden, Access and Value Team |
| --- | --- |
| Attention | Samira Toghanian (samira.toghanian@pfizer.com) |
| Prepared by | Viti Science AB |
| Reference | Mate Szilcz (mate.szilcz@vitiscience.se, mate.szilcz@pfizer.com) |
| Date | 20 March 2026 |

# 1. Background

The Swedish healthcare system is organised across 21 self-governing regions, each with considerable autonomy over healthcare budgets, pharmaceutical formulary decisions, and vaccine procurement. For pharmaceutical companies operating nationally, understanding the governance structures, financial priorities, and disease burden of each region is essential for effective stakeholder engagement, market access planning, and policy dialogue.

Pfizer Sweden has identified the need for a comprehensive regional mapping that consolidates publicly available and proprietary data into a single, actionable reference. The deliverable will support strategic conversations with regional decision-makers, policymakers, the NT Council (NT-rådet), and preparations for Almedalen 2026.

# 2. Objectives

The project aims to deliver a structured overview of all 21 Swedish regions, covering:

- Healthcare governance and key decision-makers (region directors, healthcare directors, pharmaceutical committees, representatives in the collaborative group)

- Budget allocation for healthcare, social care, and pharmaceuticals (including vaccines)

- Regional demographics (population size, age distribution, urbanisation)

- Disease burden and diagnosis volumes for priority therapeutic areas

- Pharmaceutical and vaccine utilisation volumes, including per-capita usage in relation to gross regional product (GRP)

# 3. Scope: Product Focus Areas

The mapping will prioritise the following Pfizer products and therapeutic areas:

## 3.1 Vaccines

- Prevenar (pneumococcal)

- Abrysvo (RSV)

- Borrelia/Lyme vaccine (pipeline, epidemiology mapping only)

## 3.2 Oncology

- Lorbrena (lorlatinib, ALK+ NSCLC)

- Tukysa (tucatinib, HER2+ breast cancer)

- Elrexfio (elranatamab, multiple myeloma)

- Ibrance (palbociclib, HR+/HER2- breast cancer)

- Talzenna (talazoparib, BRCA-mutated breast cancer)

## 3.3 Rare Disease and Internal Medicine

- Hympavzi (marstacimab, haemophilia)

- Vyndaqel (tafamidis, transthyretin amyloid cardiomyopathy)

- Paxlovid (nirmatrelvir/ritonavir, COVID-19)

- Vydura (rimegepant, migraine)

For pipeline products without sales data (Borrelia/Lyme vaccine), the mapping will focus on regional epidemiology using data from the Public Health Agency of Sweden (Folkhälsomyndigheten). This will provide incidence rates and geographic distribution relevant to future market shaping.

## 3.4 Pipeline Therapeutic Areas

In addition to currently marketed products, the mapping will cover three therapeutic areas relevant to Pfizer’s pipeline:

- Obesity,

- Prostate cancer

- Lung cancer

For these areas, no Pfizer sales data is available. The mapping will instead focus on regional epidemiology, disease burden, using diagnosis statistics from Stocialstyrelsen and for obesity, potentially national public health survey data from the Public Health Agency. This will provide the regional baseline needed for future market shaping and launch planning.

# 4. Data Sources and Methodology

The project will draw on the following data sources:

| Data Layer | Primary Source | Availability | Notes |
| --- | --- | --- | --- |
| Key personnel | Viti Science (validated by project group) | Available, labour-intensive | 21 regions, requires verification |
| Regional budgets | SKR economic database, annual reports | Public | Some reporting lag |
| Vaccine budgets | Regional reporting | Partial | Not all regions report separately |
| Demographics | Statistics Sweden (SCB) | Open, structured | Population, age, urbanisation |
| GRP per capita | SCB regional accounts | Open | Latest available year |
| Diagnosis volumes | Socialstyrelsen (patient register, cancer register) | Public statistics | By region and ICD-10 code |
| Drug and vaccine sales | IQVIA (via project group) | Covered by Pfizer | Per region, per product |
| Epidemiology (borrelia) | Folkhälsomyndigheten, published studies | Open | Regional incidence data |
| Usage per capita vs GRP | Derived (calculated) | Derived | Analytical value-add |

IQVIA data extraction will be performed by Project group on behalf of Pfizer. Viti Science will be responsible for sourcing and integrating all public data, performing the analysis, and producing the final deliverable. National register data (Socialstyrelsen) provides total diagnosis volumes by region but does not capture molecular subtypes. Product-level IQVIA sales will serve as a proxy for subtype-specific utilisation.

# 5. Deliverable

The primary deliverable is a PowerPoint slide deck (.pptx) structured in two parts:

## Part A: National Comparative Overview

A set of thematic overview slides comparing all 21 regions on key metrics. This includes budget allocation benchmarking, demographic summaries, aggregate disease burden by therapeutic area, and pharmaceutical and vaccine spend per capita relative to GRP. These slides are designed for high-level strategic conversations and policy dialogue.

## Part B: Individual Region Profiles

One structured profile per region (21 profiles), each covering governance and key contacts, budget breakdown, demographic snapshot, diagnosis volumes for priority areas, product-level utilisation data, and per-capita usage metrics. These profiles support targeted stakeholder engagement and regional planning.

The deck will be designed for flexible use. Slides can be extracted and recombined for specific dialogues with politicians, authorities, or the NT Council, as well as for Almedalen preparations.

In addition to the slide deck, the delivery will include a supporting data appendix (Excel workbook with all source data and derived calculations) and a one-page methodology note documenting data sources, reference years, and known limitations.

# 6. Project Team and Roles

| Role | Person | Responsibility |
| --- | --- | --- |
| Project Lead | Máté Szilcz (Viti Science) | Project management, data integration, analysis, deck production, client communication |
| Pfizer Lead | Samira Toghanian (Pfizer) | Primary contact, project oversight, strategic direction |
| Stakeholder Validation | Project group (Pfizer) | Validation and supplementation of stakeholder mapping compiled by Viti Science |
| IQVIA Data | Project group (Pfizer) | Extraction and delivery of IQVIA sales data by region and product |

# 7. Timeline

The project is planned across 8 weeks, with final delivery by mid-May 2026.

| Period | Activity | Milestone |
| --- | --- | --- |
| Weeks 1–2 | Scoping workshop, data requests to project group, public data collection (SCB, SoS, SKR, FHM) | Data sources identified and collection initiated |
| Weeks 3–4 | Data integration, per-region profile construction, analytical metrics (per-capita, GRP-adjusted) | Draft data tables for all 21 regions |
| Weeks 5–6 | Slide deck build, data visualisation, design iteration | Draft deck delivered for review |
| Weeks 7–8 | Feedback incorporation, review rounds with Pfizer, final delivery | Final deliverable (mid-May 2026) |

Dependency: Timely delivery of IQVIA data extracts (by end of Week 2) from the Pfizer team is assumed. Viti Science will deliver a completed stakeholder mapping draft to the project group for validation by end of Week 2, with corrections returned by end of Week 3. Delays in data delivery may shift the timeline.

# 8. Assumptions and Limitations

- IQVIA data will be extracted and delivered by the Pfizer team at no cost to this project.

- Stakeholder and governance mapping will be researched by Viti Science using publicly available sources and validated by the project group.

- Vaccine budget data will have structural gaps. Childhood vaccines are procured centrally via Folkhälsomyndigheten, while adult vaccines (influenza, COVID-19) are procured regionally with varying budget categorisation. A complete, comparable vaccine spend per region may not be achievable for all vaccine types.

- Public data from SCB, Socialstyrelsen, and FHM may have a 1 to 2 year reporting lag.

- For rare disease indications (ATTR cardiomyopathy, haemophilia), regional patient numbers may be too small for Socialstyrelsen to report at regional level. These indications will be presented using national estimates where regional data is suppressed.

- Diagnosis volumes from national registers reflect total disease burden (e.g., all breast cancer, all lung cancer). Molecular subtypes (ALK+, HER2+, HR+/HER2-, BRCA) are not available from register data. Product-level IQVIA sales data will serve as a proxy for subtype-specific volumes.

- The deliverable is a one-off slide deck. Periodic updates can be proposed as a separate engagement.

- Up to two rounds of revision are included in the estimate. Additional revision rounds may require scope adjustment.

Máté Szilcz, PhD  |  CEO & Founder

mate.szilcz@vitiscience.se  |  +46 72 171 9505

www.vitiscience.se